## Usage Manual
WBS and Estimates v1.5 — Usage Manual
A presale/delivery estimation pack. PERT 3-point estimation per discipline, reconciled into one resource and cost model with profitability and a maintenance run-rate.
Document conventions
| Color coding | GRAY = hardcoded input (do not edit). BLUE = computed (do not edit). GREEN = editable (estimator inputs go here). YELLOW = epic / section / guidance row. ORANGE = validation warning (P/O ratio > 5 or O>ML>P).
| Per-tab guidance | Every tab has a yellow guidance block at the top with Purpose / How to use / Inputs / Outputs / Linked tabs. Read it before editing.
| Named ranges | Coefficients and enums are named ranges (RefBugFix, RefRate, EnumRoles, ...). Edit them on the Input Data tab; references update everywhere.
Methodology
| PERT formulas | Expected = (O + 4*ML + P)/6. StdDev = (P - O)/6. Variance = StdDev^2. Project Buffer on the Buffers tab = Subtotal + Z * sqrt(Sum(Variance)). Z = 0 (50%) / 1 (84%) / 2 (97%) confidence.
| Two layers of risk | (1) Per-line Contingency on every Est tab (Apply = Yes => add ML * default_contingency to Expected). Use this for SPECIFIC uncertain items (KYC, blockchain, vendor APIs). (2) Project-wide PERT Z-score buffer on the Buffers tab. Use this for OVERALL confidence interval on the SOW.
| Augmentation coefficients | On the WBS tab, Augmented = Base * (1 + UnitTest + IntegrationTest + CodeReview). Bugfix / Documentation / Communication are added on the Buffers tab as % of Buffered total.
| QA derivation | Manual QA = (BE + FE) * RefManualQA. AQA = (BE + FE) * RefAQA. v1.5 fixes the v1.4 bug where QA variance was not propagated — Z-score buffer now applies to QA too. Alternative: use the QA Estimation tab for a per-stream QA WBS and override these coefficients.
| Cost layering | (a) FTE cost from Headcount and Cost (rate looked up by Role x Seniority x Location on Rates tab; falls back to RefRate if no match). (b) Fixed Costs tab adds lump sums (pen test, audit, ...). (c) Maintenance tab models post go-live monthly run rate. (d) Internal Cost & Profitability gives margin.
Workflow — order of operations
| Step 1 — Set context | Fill Check-list (estimator names + reviews). Fill Solution Context & Sizing (#products, channels, integrations, durations, risks). Without these the number is unfalsifiable.
| Step 2 — Build WBS | On WBS and Estimates, replace seed rows with your epics and user stories. Use stable IDs (E-1, US-1.3). Per row: enter O/ML/P for BE and FE, set Include / Phase / Milestone, write Assumptions / Description / Out of Scope / Jira link. Validation will flag P/O > 5 or O>ML>P in orange.
| Step 3 — Apply per-line contingency | For HIGH-UNCERTAINTY rows set Apply Contingency = Yes. The default contingency is per-discipline (BA 20%, Arch 30%, QA 15%, DevOps 30%, PM 20%, UIUX 20%); on WBS the contingency is entered manually per row.
| Step 4 — Fill discipline tabs | BA / Arch / QA / DevOps / PM / UIUX. Same column shape on each tab. Mark Include / Phase per item. Items left at zero hours are still in the catalogue but excluded from totals.
| Step 5 — Set Z-score | On Buffers & Non-Dev Activities choose Z (0..2). Higher = more buffer = more conservative SOW. Default 1.0 (84% CI).
| Step 6 — Maintain Rates | Edit Rates tab: rows are (Role x Seniority x Location => $/h). Headcount and Cost looks up rate via INDEX/MATCH. If no row matches the resource's (Role, Seniority, Location), the formula falls back to RefRate.
| Step 7 — Allocate resources | On Headcount and Cost, add a row per resource with Role / Seniority / Location / Headcount / Allocation / Start Week / End Week. The right-hand 'Estimated vs Allocated' panel computes Delta Hours per role; minimize the absolute value.
| Step 8 — Add fixed costs | On Fixed Costs add 3rd-party items (pen test, audit, perf test, KYC vendor licenses, cloud cost). Set Include = Included / Not included / Post-MVP.
| Step 9 — Verify margin | On Internal Cost & Profitability check 'Project Profitability (build)' is at or above the desired threshold. If not, revisit Rates / seniority mix / scope.
| Step 10 — Plan maintenance | Fill the Maintenance tab. Annual Run-rate is exposed; quote it separately in the SOW.
| Step 11 — Use reports | Epic Weight ranks epics by cost (sponsor view). Monthly Cost Roll-out shows cash-flow profile. WBS Comparison stores snapshots so scope creep between versions is visible.
| Step 12 — Peer review & sign-off | Update Check-list reviews to 'Yes' once Architecture / Design / BA / QA / DevOps / Estimation peer reviews complete. DM/PM final sign-off last.
Tab index
| Check-list | WHO estimated and WHAT was reviewed. Use it as the audit trail.
| Solution Context & Sizing | WHY the number is what it is. Records the assumptions the estimate is conditioned on.
| WBS and Estimates | Hierarchical Epic > User Story with BE/FE PERT estimates and per-row metadata.
| BA / Arch / QA / DevOps / PM / UIUX Estimation | Per-discipline WBS. Replace the catalogue with reality and toggle Include/Phase per item.
| Buffers & Non-Dev Activities | Applies PERT Z-score, Bugfix/Doc/Communication coefficients, derives MQA/AQA, adds discipline roll-ups.
| Rates | Role x Seniority x Location rate card.
| Headcount and Cost | Resource allocation grid with rate lookup; reconciles allocated vs estimated.
| Internal Cost & Profitability | Salary + tax + overhead per resource; project profitability.
| Monthly Cost Roll-out | Spreads allocated cost across months for cash-flow.
| Fixed Costs | Lump-sum / 3rd-party costs included or excluded from the proposal.
| Maintenance | Post go-live monthly + annual run-rate.
| Epic Weight | Cost-by-epic ranking for sponsor conversations.
| WBS Comparison | Side-by-side WBS snapshots; deltas between versions.
| Input Data | Global coefficients, blended-rate fallback, enums for dropdowns.
Field glossary
| Include | Included = goes into totals & SOW. Not included = stays in catalogue but excluded. Post-MVP = parked. Select = decision pending.
| Project Phase | Discovery / Implementation / Post-MVP Enhancement / Maintenance. Drives where the row's hours land in the cost roll-out.
| Apply Contingency | Yes/No per row. When Yes, default contingency % multiplies Most Likely and is added to Expected to form Final Expected.
| Final Expected | Expected + Contingency. This is what feeds totals and downstream tabs.
| Seniority Index | Roughly: average external rate divided by RefRate. > 1 means the team is more senior than the blended baseline; < 1 means more junior.
| Delta Hours | Allocated Hours minus Estimated Hours per role. Negative = under-staffed (project will run long). Positive = over-staffed (cost waste).
Defensibility checklist
| Before sending the estimate | (1) Check-list filled. (2) Solution Context filled. (3) No orange validation warnings on WBS. (4) Discipline tabs reviewed by their respective leads. (5) Profitability >= threshold. (6) Peer review done. (7) Sponsor view (Epic Weight) sanity-checked. (8) Maintenance discussed even if not in scope.

## Check-list
Check-list — Estimator team & reviews
Purpose: | Audit trail for the estimate. Records WHO contributed each role's number and WHICH reviews have been completed. Without it, the workbook is anonymous and undefendable.
How to use: | Fill the names per role. As each review (Architecture / Design / BA / QA / DevOps / Peer / DM-PM sign-off) completes, set State = Yes and add Date + Reviewer. Mandatory calculations at the bottom point to where each KPI lives so a reviewer can verify them.
Inputs: | Names (manual). Review states / dates / reviewers (manual). KPI values can be linked from other tabs.
Outputs: | A single-page record that proves who estimated and who signed off.
Linked tabs: | Mandatory calculations point to: Internal Cost & Profitability, Headcount and Cost, Maintenance.
| Role / responsibility | Last name, First name
DM responsible for estimation
PM responsible for estimation (if any)
Estimation Team
| Role | Last name, First name
Solution Architect
Software Architect
Data Architect
Lead BA / BA
Lead QA / QA
DevOps
Designer (UI/UX)
Front-end Web Developer
Front-end Mobile Developer
Back-end Developer
Other
Reviews
| Review type | State | Date | Reviewer
| Architecture Review | Yes
Design Review (if any)
BA / Requirements Review
| QA Strategy Review | In progress
DevOps / Infra Review
Estimation Peer Review
Final Sign-off (DM/PM)
Mandatory calculations
| Calculation | Value | Source
| Discovery Phase Profitability (if any) |  | Internal Cost & Profitability
| Proposed solution price profitability |  | Internal Cost & Profitability
| Seniority Index |  | Internal Cost & Profitability
| Total Hours (Build) |  | Headcount and Cost
| Total Hours (Maintenance, monthly) |  | Maintenance
| Total Cost (Build) |  | Headcount and Cost
| Project Duration (weeks) |  | Headcount and Cost
| Peak FTE |  | Headcount and Cost

## Solution Context & Sizing
Solution Context & Sizing
Purpose: | Records the assumptions the estimate is conditioned on. If any of these change materially after the SOW is signed, the estimate must be revisited.
How to use: | Fill the Value column for each parameter. Discuss with the client; if a parameter is unknown, mark it 'TBD' and add it to the top risks. Use this tab as the cover sheet of the estimate when sharing externally.
Inputs: | Manual values from estimator + client conversations.
Outputs: | An immutable record of the scoping context at the moment the estimate was made.
Linked tabs: | Drives Apply Contingency = Yes decisions on every Est tab. Top risks here become the contingency drivers there.
Section | Parameter | Value / description | Notes
Scope | Products |  | e.g. 1 product (eWallet, marketplace, ...)
Scope | Customers / customer categories |  | B2C / B2B / Internal
Scope | User roles |  | e.g. End-user, Business user, Admin
Scope | Channels |  | Web, iOS, Android, integrations
Scope | Domain logic complexity |  | Simple CRUD / Domain heavy / Regulated
Scope | Integrations (count) |  | 5-15 integrations, list known ones
Scope | Vendor / 3rd-party products |  | Set up by vendor or by us?
Scope | Major features (epics) |  | 10-15 epics typical
Infra | Infrastructure model |  | Public cloud / On-prem / Hybrid / Multi-region
Infra | Data residency / compliance |  | GDPR, HIPAA, PCI-DSS, SoX, ...
Infra | Expected load |  | users, RPS, data volume
Infra | Availability target |  | SLA, RTO, RPO
Phases | Discovery duration |  | e.g. 1 month (3 weeks active work)
Phases | Implementation duration |  | e.g. 5 months
Phases | Maintenance / run-rate after go-live |  | Yes / No, how many months
Risks | Top 3 estimation risks |  | drives per-line Apply Contingency = Yes
Risks | Known unknowns
Risks | Hard assumptions |  | things we believe but did not verify

## WBS and Estimates
WBS and Estimates
Purpose: | The product WBS — Epic > User Story hierarchy with PERT 3-point estimates for Back-End and Front-End. Per-row metadata makes the estimate defensible: every row carries an Include flag, Project Phase, Milestone, Assumptions, Description, Out of Scope, Dependencies, Comments and Jira link.
How to use: | (1) Add Section / Epic / User Story rows. Use stable IDs (E-1, US-1.3) — Epic Weight and WBS Comparison match by ID prefix. (2) Per US row, enter O / ML / P in hours for BE and FE. Augmented columns auto-add UnitTest+IntegrationTest+CodeReview. Expected, StdDev and Variance are PERT-derived. (3) Set Apply Contingency = Yes only on rows where you want to load extra hours; enter Contingency BE / FE manually. (4) Pick Include (Included / Not included / Post-MVP / Select), Phase, Milestone. (5) Fill Assumptions / Description / Out of Scope / Dependencies / Comments / Jira link. (6) Validation will highlight rows in ORANGE if P/O > 5 or O>ML>P — fix or comment.
Inputs: | O / ML / P per row (hours). Include / Phase / Milestone / Apply Contingency / Contingency BE/FE / metadata.
Outputs: | Expected BE / FE per row, StdDev/Variance per row. Sums of P (col P, BE Expected) and Q (FE Expected), and S/U (variance) feed Buffers & Non-Dev Activities.
Linked tabs: | Buffers & Non-Dev Activities (consumes Expected and Variance). Epic Weight (groups by ID prefix). WBS Comparison (joins by ID). Headcount and Cost (via Buffers totals).
Hierarchy | ID | Decomposition Item | Backend, h |  |  | Frontend, h |  |  | Augmented Backend, h |  |  | Augmented Frontend, h |  |  | Expected Implementation Back-End (man/h) | Expected Implementation Front-End (man/h) | StdDev BE | Variance BE | StdDev FE | Variance FE | Apply Contingency | Contingency, h (BE) | Contingency, h (FE) | Include | Project Phase | Milestone | Assumptions | Description / Scope | Out of Scope | Dependencies | Comments | Jira / Ticket Link
Hierarchy | ID | Decomposition Item | O | ML | P | O | ML | P | Augmented O | Augmented ML | Augmented P | Augmented O | Augmented ML | Augmented P | Expected BE | Expected FE | StdDev BE | Variance BE | StdDev FE | Variance FE | Apply Contingency | Contingency BE | Contingency FE | Include | Phase | Milestone | Assumptions | Description / Scope | Out of Scope | Dependencies | Comments | Jira / Ticket Link
Section |  | Infrastructure & Foundations
UserStory | INF-1.1 | Solution setup (repos, project templates) | 8 | 16 | 32 | 6 | 12 | 20 | [12 empty] | No | 0 | 0 | Included | Implementation | M1 |  | Bootstrap repositories, project templates, CI seed
UserStory | INF-1.2 | Local infrastructure setup | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | No | 0 | 0 | Not included | Implementation | M1 |  |  |  |  | Covered in DevOps tab
UserStory | INF-1.3 | CI/CD setup | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | No | 0 | 0 | Not included | Implementation | M1 |  |  |  | DevOps | Covered in DevOps tab
UserStory | INF-1.4 | Static code analysis | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | No | 0 | 0 | Not included | Implementation | M1 |  |  |  |  | Covered in DevOps tab
Section |  | Product Scope
Epic | E-1 | Authorization
UserStory | US-1.1 | Onboarding | 0 | 0 | 0 | 2 | 8 | 16 | [12 empty] | No | 0 | 0 | Included | Implementation | M1
UserStory | US-1.2 | Accept Terms of Use | 0 | 0 | 0 | 1 | 3 | 4 | [12 empty] | No | 0 | 0 | Included | Implementation | M1
UserStory | US-1.3 | Sign Up (email/phone/SSO) | 16 | 24 | 32 | 16 | 24 | 32 | [12 empty] | No | 0 | 0 | Included | Implementation | M1 | Google/Microsoft/Apple SSO
UserStory | US-1.4 | Login | 8 | 16 | 24 | 8 | 16 | 24 | [12 empty] | No | 0 | 0 | Included | Implementation | M1
UserStory | US-1.5 | Reset password | 8 | 16 | 24 | 4 | 8 | 16 | [12 empty] | No | 0 | 0 | Included | Implementation | M1
UserStory | US-1.6 | Logout | 2 | 4 | 8 | 2 | 4 | 8 | [12 empty] | No | 0 | 0 | Included | Implementation | M1
UserStory | US-1.7 | 2FA setup | 16 | 32 | 48 | 8 | 16 | 24 | [12 empty] | No | 0 | 0 | Included | Implementation | M2 | TOTP via authenticator + SMS fallback
Epic | E-2 | Profile Management
UserStory | US-2.1 | View profile info | 4 | 8 | 16 | 4 | 8 | 12 | [12 empty] | No | 0 | 0 | Included | Implementation | M1
UserStory | US-2.2 | Edit personal details | 8 | 16 | 24 | 12 | 20 | 32 | [12 empty] | No | 0 | 0 | Included | Implementation | M1
UserStory | US-2.3 | Change password | 4 | 8 | 16 | 4 | 8 | 12 | [12 empty] | No | 0 | 0 | Included | Implementation | M1
UserStory | US-2.4 | Manage notification preferences | 8 | 16 | 24 | 4 | 8 | 12 | [12 empty] | No | 0 | 0 | Included | Implementation | M2
UserStory | US-2.5 | Delete account | 8 | 16 | 24 | 4 | 8 | 12 | [12 empty] | No | 0 | 0 | Included | Implementation | M2
Epic | E-3 | Wallet (sample regulated/financial epic)
UserStory | US-3.1 | Setup wallet | 16 | 24 | 40 | 24 | 40 | 60 | [12 empty] | No | 0 | 0 | Included | Implementation | M2 | custodial wallet, KMS-backed
UserStory | US-3.2 | Buy tokens | 16 | 24 | 40 | 12 | 20 | 32 | [12 empty] | No | 0 | 0 | Included | Implementation | M2 | Stripe + crypto on-ramp
UserStory | US-3.3 | Sell tokens | 16 | 24 | 40 | 8 | 12 | 24 | [12 empty] | No | 0 | 0 | Included | Implementation | M3
UserStory | US-3.4 | View transactions | 12 | 20 | 32 | 12 | 16 | 24 | [12 empty] | No | 0 | 0 | Included | Implementation | M2
UserStory | US-3.5 | KYC initiate / upload ID / verify | 16 | 32 | 64 | 8 | 16 | 24 | [12 empty] | No | 0 | 0 | Included | Implementation | M3 | 3rd-party KYC vendor (Onfido/SumSub)

## BA Estimation
Business Analysis Estimation
Purpose: | Catalogue of BA deliverables (Vision & Scope, USM, RACI, BPMN, Class diagrams, prototypes, benchmarking, ...) with PERT estimates per item. Replaces the v1.4 assumption that BA effort equals 0.25 FTE.
How to use: | (1) Walk down the catalogue. (2) Set O/ML/P for items you'll deliver, leave others at 0. (3) Set Include = Not included for items the client did not buy (they stay in the catalogue but excluded from totals). (4) Use Apply Contingency = Yes on items with vague requirements (typical 20% default). (5) Mark Phase = Discovery / Implementation / Post-MVP / Maintenance.
Inputs: | O/ML/P per row, Apply Contingency Y/N, Include, Phase, Deliverable, Description, Assumptions, Notes.
Outputs: | Final Expected per row. Included sum (col I where Include=Included) flows to Buffers & Non-Dev Activities and from there to Headcount and Cost as the BA estimated hours.
Linked tabs: | Buffers & Non-Dev Activities (BA roll-up). Headcount and Cost (BA estimated hours).
Default contingency: | 0.2 | (used when Apply Contingency = Yes; multiplied by Most Likely)
Per-line PERT estimate for BA deliverables. Default contingency 20% applied when Apply Contingency = Yes.
ID | Service / Activity | Optimistic | Most Likely | Pessimistic | Expected | Apply Contingency | Contingency | Final Expected | Include | Project Phase | Deliverable | Description / Scope | Assumptions | Notes
| TOTALS | [7 empty] | (only Included counted at right)
BA-1 | Discovery deliverables
BA-1.1 | Vision & Scope document | 8 | 16 | 24 |  | Yes |  |  | Included | Discovery | Vision & Scope doc | Background, Business Opportunity, Objectives, Risks, Vision Statement, Major Features, Assumptions, Stakeholder Profiles, Operating Environment, Glossary
BA-1.2 | User Story Map (USM) | 16 | 32 | 48 |  | Yes |  |  | Included | Discovery | USM | Visualization of the product backbone across user journey
BA-1.3 | Roles & Permissions Matrix | 8 | 12 | 20 |  | Yes |  |  | Included | Discovery | RBAC matrix | Roles, role-related features, permission grid
BA-1.4 | WBS / Feature list adjustment | 4 | 8 | 16 |  | No |  |  | Included | Discovery | MVP / Post-MVP feature list
BA-1.5 | Initial Sprint Backlog | 16 | 24 | 40 |  | Yes |  |  | Included | Discovery | Initial Backlog | Prioritized, DoR-ready USs for first sprints
BA-1.6 | BPMN diagrams (key processes) | 16 | 32 | 48 |  | Yes |  |  | Included | Discovery | BPMN diagrams
BA-1.7 | Interactive prototypes (key flows) | 16 | 24 | 40 |  | No |  |  | Not included | Discovery | Figma prototypes | Coordinated with UI/UX tab
BA-1.8 | Context Diagram | 8 | 12 | 24 |  | No |  |  | Included | Discovery | Context diagram
BA-1.9 | Class diagram (high level) | 8 | 12 | 24 |  | No |  |  | Included | Discovery | Class diagram
BA-1.10 | State machine diagram | 8 | 16 | 32 |  | No |  |  | Included | Discovery | State machine
BA-1.11 | Benchmarking / competitor analysis | 16 | 32 | 48 |  | No |  |  | Not included | Discovery
BA-1.12 | Stakeholder Matrix / Glossary / Communication plan | 4 | 8 | 12 |  | No |  |  | Included | Discovery
BA-2 | Implementation deliverables
BA-2.1 | Refining backlog (per sprint) | 4 | 8 | 12 |  | No |  |  | Included | Implementation | Refined backlog | Per sprint over implementation duration
BA-2.2 | Acceptance criteria authoring | 4 | 8 | 12 |  | No |  |  | Included | Implementation
BA-2.3 | Change request analysis | 4 | 8 | 16 |  | Yes |  |  | Included | Implementation
BA-2.4 | Demo support / UAT support | 4 | 8 | 16 |  | No |  |  | Included | Implementation

## Arch Estimation
Architecture Estimation (SA + Software A)
Purpose: | Catalogue of architecture deliverables — Architectural Drivers (AVD), Solution Architecture views (Context/Container/Component/Deployment), Decision/Risk records, Operation plan, Implementation roadmap. 30% contingency reflects design uncertainty.
How to use: | (1) Per item, set O/ML/P. (2) Items left empty stay in the catalogue as a checklist of what was considered but not estimated (mark Include = Not included). (3) Use Apply Contingency = Yes for items requiring discovery workshops or third-party APIs. (4) Compliance items (OWASP, GDPR, PCI-DSS, HIPAA, SoX) are off by default — switch on if applicable.
Inputs: | O/ML/P per row, Apply Contingency Y/N, Include, Phase, Deliverable, Description, Assumptions.
Outputs: | Architecture roll-up flows to Buffers tab and then Headcount and Cost as 'Architecture (SA+SwA)' estimated hours.
Linked tabs: | Buffers & Non-Dev Activities (Architecture roll-up). Headcount and Cost.
Default contingency: | 0.3 | (used when Apply Contingency = Yes; multiplied by Most Likely)
Solution & Software Architecture deliverables. Higher 30% contingency reflects design uncertainty.
ID | Service / Activity | Optimistic | Most Likely | Pessimistic | Expected | Apply Contingency | Contingency | Final Expected | Include | Project Phase | Deliverable | Description / Scope | Assumptions | Notes
| TOTALS | [7 empty] | (only Included counted at right)
ARC-1 | Architectural Drivers (AVD)
ARC-1.1 | Business Goals | 2 | 2.5 | 3 |  | No |  |  | Included | Discovery | AVD: Business Goals
ARC-1.2 | Major Features | 2 | 2.5 | 3 |  | No |  |  | Included | Discovery
ARC-1.3 | Design Constraints | 2 | 2.5 | 3 |  | No |  |  | Included | Discovery
ARC-1.4 | Architectural Concerns | 2 | 2.5 | 3 |  | No |  |  | Included | Discovery
ARC-1.5 | Quality Attributes (cross-cutting) | 8 | 10 | 12 |  | Yes |  |  | Included | Discovery |  | Availability, Performance, Observability, Scalability, Localization, Fault Tolerance, Recoverability, Security (App + Code), Extendability, Maintainability
ARC-1.6 | Compliance scope (OWASP/GDPR/PCI/HIPAA/SoX) | 0 | 0 | 0 |  | No |  |  | Not included | Discovery |  | Estimated separately per applicable regulation
ARC-2 | Solution Architecture
ARC-2.1 | System Context View | 2 | 4 | 6 |  | No |  |  | Included | Discovery
ARC-2.2 | Container View | 4 | 6 | 8 |  | No |  |  | Included | Discovery
ARC-2.3 | Component View — Front-end | 1 | 3 | 4 |  | No |  |  | Not included | Discovery
ARC-2.4 | Component View — Back-end | 3 | 6 | 8 |  | Yes |  |  | Included | Discovery
ARC-2.5 | Epic-level architectural design | 16 | 18 | 20 |  | Yes |  |  | Included | Discovery
ARC-2.6 | Deployment View | 4 | 8 | 10 |  | Yes |  |  | Included | Discovery
ARC-2.7 | Decision View / ADRs | 4 | 6 | 8 |  | No |  |  | Not included | Discovery
ARC-2.8 | Risk View / Risk Record | 4 | 6 | 8 |  | No |  |  | Included | Discovery
ARC-3 | Operation plan
ARC-3.1 | Infrastructure model | 2 | 5 | 4 |  | Yes |  |  | Included | Discovery
ARC-3.2 | Continuous integration / continuous delivery | 2 | 5 | 4 |  | Yes |  |  | Included | Discovery
ARC-3.3 | Monitoring / Observability | 2 | 5 | 4 |  | Yes |  |  | Included | Discovery
ARC-3.4 | Secure SDLC concepts | 2 | 5 | 4 |  | No |  |  | Included | Discovery
ARC-3.5 | Backup & restore | 2 | 5 | 4 |  | No |  |  | Included | Discovery
ARC-4 | Implementation Roadmap
ARC-4.1 | Implementation Milestones | 2 | 3 | 4 |  | No |  |  | Included | Discovery
ARC-4.2 | Development technology stack | 1 | 1.5 | 2 |  | No |  |  | Included | Discovery
ARC-4.3 | Estimation: structure & validation | 8 | 11 | 10 |  | No |  |  | Included | Discovery
ARC-4.4 | Development team skillset | 1 | 1.5 | 2 |  | No |  |  | Included | Discovery
ARC-5 | Discovery workshops
ARC-5.1 | Discovery questions preparation | 8 | 12 | 16 |  | Yes |  |  | Included | Discovery
ARC-5.2 | AVD draft / 1st review | 8 | 12 | 16 |  | No |  |  | Included | Discovery
ARC-5.3 | Internal peer review | 4 | 6 | 8 |  | No |  |  | Included | Discovery
ARC-6 | Implementation phase support
ARC-6.1 | Architecture governance & ADRs | 8 | 16 | 24 |  | No |  |  | Included | Implementation
ARC-6.2 | Tech debt review / risks reassessment | 4 | 8 | 16 |  | No |  |  | Included | Implementation
ARC-6.3 | Sprint architecture support | 4 | 8 | 12 |  | No |  |  | Included | Implementation

## QA Estimation
QA Estimation (per stream)
Purpose: | Defensible QA WBS split by stream: Front-end / Back-end / Mobile / Automation. Each stream covers System Config, Test Env, Strategy, Test Data, Test Case Design, Functional, Non-functional, Database, Change-related (Smoke/Regression), Test Closure.
How to use: | (1) Per stream, fill O/ML/P for activities relevant to your project. (2) Disable streams that don't apply by setting Include = Not included on every row of that stream. (3) Automation block defaults to Post-MVP — switch to Included if AQA is in scope for build. (4) The Buffers tab pulls the QA Estimation Included sum and uses it instead of the 15% MQA coefficient when populated; otherwise it falls back to the coefficient-based MQA/AQA derivation.
Inputs: | O/ML/P per row, Apply Contingency Y/N, Include, Phase, Deliverable, Description.
Outputs: | QA roll-up (per-stream and total). Feeds Buffers tab QA row.
Linked tabs: | Buffers & Non-Dev Activities (QA from this tab vs MQA/AQA coefficient). Headcount and Cost (Manual QA / AQA estimated hours).
Default contingency: | 0.15 | (used when Apply Contingency = Yes; multiplied by Most Likely)
Streams: FE / BE / Mobile / Automation. Use this tab for a defensible per-stream QA WBS in addition to (or in place of) the flat 15% coefficient from v1.4.
ID | Service / Activity | Optimistic | Most Likely | Pessimistic | Expected | Apply Contingency | Contingency | Final Expected | Include | Project Phase | Deliverable | Description / Scope | Assumptions | Notes
| TOTALS | [7 empty] | (only Included counted at right)
QA-FE | QA — Front-end stream
QA-FE.1 | System Configuration | 5 | 6 | 7 |  | No |  |  | Included | Discovery | Task / bug-tracking config
QA-FE.2 | Test Environment Setup | 6 | 8 | 12 |  | No |  |  | Included | Discovery
QA-FE.3 | Test Strategy & Test Plan | 10 | 14 | 18 |  | Yes |  |  | Included | Discovery | Test Strategy + Test Plan
QA-FE.4 | Documentation Investigation | 50 | 60 | 70 |  | No |  |  | Included | Implementation
QA-FE.5 | Test Data preparation | 70 | 90 | 120 |  | No |  |  | Included | Implementation
QA-FE.6 | Test Case design | 110 | 140 | 170 |  | No |  |  | Included | Implementation
QA-FE.7 | Functional Testing (E2E) | 90 | 120 | 140 |  | Yes |  |  | Included | Implementation
QA-FE.8 | Non-functional Testing (UI/UX, Docs) | 120 | 130 | 160 |  | No |  |  | Included | Implementation
QA-FE.9 | Change-related (Smoke/Regression/Critical Path) | 110 | 140 | 160 |  | Yes |  |  | Included | Implementation
QA-FE.10 | Test Closure | 40 | 50 | 65 |  | No |  |  | Included | Implementation
QA-BE | QA — Back-end stream
QA-BE.1 | System Configuration | 8 | 14 | 16 |  | No |  |  | Not included | Discovery
QA-BE.2 | Test Environment Setup | 8 | 14 | 16 |  | No |  |  | Not included | Discovery
QA-BE.3 | Database (data integrity, migrations) | 8 | 12 | 14 |  | No |  |  | Not included | Discovery
QA-BE.4 | Documentation Investigation | 160 | 180 | 190 |  | No |  |  | Included | Implementation
QA-BE.5 | Test Data preparation | 140 | 170 | 180 |  | No |  |  | Included | Implementation
QA-BE.6 | Test Case design | 270 | 290 | 330 |  | No |  |  | Included | Implementation
QA-BE.7 | Database Testing | 190 | 230 | 250 |  | No |  |  | Included | Implementation
QA-BE.8 | Functional Testing (Integration / API) | 280 | 300 | 320 |  | Yes |  |  | Included | Implementation
QA-BE.9 | Non-functional Testing (Docs) | 200 | 240 | 260 |  | No |  |  | Included | Implementation
QA-BE.10 | Change-related (Smoke/Regression) | 280 | 320 | 350 |  | Yes |  |  | Included | Implementation
QA-BE.11 | Test Closure | 110 | 120 | 140 |  | No |  |  | Included | Implementation
QA-MOB | QA — Mobile stream
QA-M.1 | System Configuration | 8 | 14 | 18 |  | No |  |  | Not included | Discovery
QA-M.2 | Test Environment Setup | 6 | 8 | 10 |  | No |  |  | Not included | Discovery
QA-M.3 | Documentation Investigation | 70 | 90 | 110 |  | No |  |  | Included | Implementation
QA-M.4 | Test Data | 50 | 60 | 90 |  | No |  |  | Included | Implementation
QA-M.5 | Test Case design | 180 | 210 | 230 |  | No |  |  | Included | Implementation
QA-M.6 | Functional Testing | 150 | 180 | 220 |  | Yes |  |  | Included | Implementation
QA-M.7 | Non-functional Testing (devices, OS, install) | 80 | 100 | 130 |  | No |  |  | Included | Implementation
QA-M.8 | Change-related (Smoke/Regression) | 230 | 260 | 290 |  | Yes |  |  | Included | Implementation
QA-M.9 | Test Closure | 60 | 75 | 90 |  | No |  |  | Included | Implementation
QA-AUT | QA — Automation (optional)
QA-A.1 | Framework design & setup | 0 | 0 | 0 |  | No |  |  | Post-MVP | Post-MVP Enhancement
QA-A.2 | Environment Setup | 0 | 0 | 0 |  | No |  |  | Post-MVP | Post-MVP Enhancement
QA-A.3 | CI/CD integration | 0 | 0 | 0 |  | No |  |  | Post-MVP | Post-MVP Enhancement
QA-A.4 | Test development & execution | 0 | 0 | 0 |  | No |  |  | Post-MVP | Post-MVP Enhancement

## DevOps Estimation
DevOps Estimation
Purpose: | Cloud-agnostic DevOps WBS: cost modelling, repo/IAM/CI tooling, environment build (Dev/Test/Stage/Prod), SSDLC pipelines, monitoring, backup/DR. Replaces the v1.4 single 'DevOps' role line with no hours.
How to use: | (1) Estimate Discovery cost-modelling activities first — they shape the cloud bill. (2) For environment rows, repeat the block per environment (Dev/Test/Stage/Prod). (3) Apply Contingency = Yes on cloud-vendor-dependent items (DNS, SSL, KMS, networking) where vendor surprises bite. (4) Toggle iOS/Android pipelines off if not applicable.
Inputs: | O/ML/P per row, Apply Contingency Y/N, Include, Phase, Deliverable.
Outputs: | DevOps roll-up flows to Buffers and Headcount and Cost.
Linked tabs: | Buffers & Non-Dev Activities (DevOps roll-up). Headcount and Cost (DevOps estimated hours). Fixed Costs (cloud bill — typically reflected as separate line items).
Default contingency: | 0.3 | (used when Apply Contingency = Yes; multiplied by Most Likely)
Cloud-agnostic DevOps catalogue. 30% default contingency reflects environment / vendor uncertainty.
ID | Service / Activity | Optimistic | Most Likely | Pessimistic | Expected | Apply Contingency | Contingency | Final Expected | Include | Project Phase | Deliverable | Description / Scope | Assumptions | Notes
| TOTALS | [7 empty] | (only Included counted at right)
DO-1 | Discovery — cost / sizing
DO-1.1 | Estimation of infra cost (10k MAU baseline) | 10 | 10 | 8 |  | Yes |  |  | Included | Discovery | Infra cost model
DO-1.2 | Additional services costs | 5 | 5 | 4 |  | Yes |  |  | Included | Discovery
DO-1.3 | Cost optimization options | 8 | 11 | 11 |  | Yes |  |  | Included | Discovery
DO-1.4 | Customer presentation of cost model | 3 | 4 | 4 |  | Yes |  |  | Included | Discovery
DO-2 | Implementation — preparing tooling
DO-2.1 | Pre-flight artefact check | 2 | 3 | 2 |  | No |  |  | Included | Implementation
DO-2.2 | Setup repositories (VCS) | 2 | 3 | 2 |  | No |  |  | Included | Implementation
DO-2.3 | Setup domain names & DNS | 2 | 3 | 2 |  | Yes |  |  | Included | Implementation
DO-2.4 | IAM roles for team members | 4 | 6 | 4 |  | No |  |  | Included | Implementation
DO-2.5 | Package registry | 2 | 2 | 2 |  | No |  |  | Included | Implementation
DO-2.6 | CI/CD management system | 8 | 11 | 8 |  | No |  |  | Included | Implementation
DO-2.7 | Quality gate analyzer | 3 | 4 | 3 |  | Yes |  |  | Included | Implementation
DO-2.8 | OWASP / dependency scanning | 8 | 11 | 8 |  | Yes |  |  | Included | Implementation
DO-2.9 | IaC tools setup (Terraform/Pulumi) | 8 | 11 | 8 |  | No |  |  | Included | Implementation
DO-2.10 | PaaS framework adaptation | 24 | 24 | 24 |  | Yes |  |  | Included | Implementation
DO-3 | Environments — Development
DO-3.1 | Dev account setup | 2 | 3 | 3 |  | Yes |  |  | Included | Implementation
DO-3.2 | FE deployment in Dev | 3 | 4 | 4 |  | No |  |  | Included | Implementation
DO-3.3 | BE infrastructure (containers/K8s) | 16 | 16 | 24 |  | No |  |  | Included | Implementation
DO-3.4 | VPC / subnets / security groups | 2 | 3 | 3 |  | No |  |  | Included | Implementation
DO-3.5 | VPN access | 8 | 8 | 10 |  | No |  |  | Included | Implementation
DO-3.6 | ALB / target groups / WAF | 6 | 6 | 9 |  | No |  |  | Included | Implementation
DO-3.7 | Object storage | 1 | 2 | 2 |  | Yes |  |  | Included | Implementation
DO-3.8 | Relational DB | 6 | 6 | 8 |  | Yes |  |  | Included | Implementation
DO-3.9 | Non-relational DB | 4 | 4 | 6 |  | Yes |  |  | Included | Implementation
DO-3.10 | Cache (ElastiCache/Redis) | 5 | 5 | 7 |  | Yes |  |  | Included | Implementation
DO-3.11 | CDN / distribution / cert | 3 | 5 | 5 |  | Yes |  |  | Included | Implementation
DO-4 | Environments — Test / Stage / Prod
DO-4.1 | Test environment build | 16 | 24 | 32 |  | Yes |  |  | Included | Implementation
DO-4.2 | Stage environment build | 16 | 24 | 32 |  | Yes |  |  | Included | Implementation
DO-4.3 | Prod environment build | 24 | 32 | 48 |  | Yes |  |  | Included | Implementation
DO-5 | SSDLC pipelines
DO-5.1 | iOS pipeline | 8 | 11 | 8 |  | Yes |  |  | Included | Implementation
DO-5.2 | Android pipeline | 8 | 8 | 8 |  | No |  |  | Included | Implementation
DO-5.3 | FE web pipeline | 6 | 6 | 8 |  | No |  |  | Included | Implementation
DO-5.4 | BE pipelines | 8 | 11 | 11 |  | No |  |  | Included | Implementation
DO-5.5 | SAST scanning | 8 | 11 | 11 |  | Yes |  |  | Included | Implementation
DO-5.6 | Docker image hardening rules | 6 | 6 | 6 |  | Yes |  |  | Included | Implementation
DO-6 | Operations & monitoring
DO-6.1 | Monitoring (metrics/logs/alerts) | 16 | 24 | 32 |  | Yes |  |  | Included | Implementation
DO-6.2 | Backup & DR drills | 8 | 12 | 16 |  | Yes |  |  | Included | Implementation
DO-6.3 | On-call runbook & paging | 4 | 8 | 12 |  | No |  |  | Included | Implementation

## PM Estimation
Project Management Estimation
Purpose: | PM activity catalogue — Discovery prestart, governance (RACI / DoR / DoD / Communication & Escalation matrices), project charter, sprint cadence, reporting, change management, closure. Replaces v1.4's flat 0.25 FTE PM allocation.
How to use: | (1) Routine items can be estimated with Most Likely only — leave O and P blank. (2) For impactful items (estimation oversight, staffing, change requests) provide all three points. (3) Recurring implementation items (PM-4.x) are PER SPRINT — multiply Most Likely by the number of sprints when copying into your project plan. (4) Apply Contingency = Yes on coordination-heavy items.
Inputs: | ML always; O/P optional; Apply Contingency Y/N; Include; Phase.
Outputs: | PM roll-up flows to Buffers and Headcount and Cost.
Linked tabs: | Buffers & Non-Dev Activities (PM roll-up). Headcount and Cost.
Default contingency: | 0.2 | (used when Apply Contingency = Yes; multiplied by Most Likely)
PM activity catalogue replaces the flat 0.25 FTE assumption. Use Pessimistic and Optimistic on impactful items; Most Likely is fine for routine items.
ID | Service / Activity | Optimistic | Most Likely | Pessimistic | Expected | Apply Contingency | Contingency | Final Expected | Include | Project Phase | Deliverable | Description / Scope | Assumptions | Notes
| TOTALS | [7 empty] | (only Included counted at right)
PM-1 | Discovery prestart
PM-1.1 | Compile input data list |  | 4 |  |  | Yes |  |  | Included | Discovery
PM-1.2 | Agree final budget / parameters |  | 8 |  |  | Yes |  |  | Included | Discovery
PM-1.3 | Demands creation |  | 3 |  |  | Yes |  |  | Included | Discovery
PM-1.4 | Staffing support |  | 24 |  |  | Yes |  |  | Included | Discovery
PM-1.5 | Internal kickoff meeting |  | 3 |  |  | Yes |  |  | Included | Discovery
PM-1.6 | 1C / org system entries |  | 3 |  |  | Yes |  |  | Included | Discovery
PM-1.7 | Jira space creation |  | 3 |  |  | Yes |  |  | Included | Discovery
PM-1.8 | Confluence space creation |  | 4 |  |  | Yes |  |  | Included | Discovery
PM-1.9 | Team chat creation |  | 1 |  |  | Yes |  |  | Included | Discovery
PM-1.10 | Onboarding page (wiki) |  | 8 |  |  | Yes |  |  | Included | Discovery
PM-2 | Discovery — governance
PM-2.1 | RACI matrix |  | 2 |  |  | Yes |  |  | Included | Discovery | RACI
PM-2.2 | Communication plan |  | 2 |  |  | Yes |  |  | Included | Discovery
PM-2.3 | Communication matrix |  | 1 |  |  | Yes |  |  | Included | Discovery
PM-2.4 | Escalation matrix |  | 1 |  |  | Yes |  |  | Included | Discovery
PM-2.5 | DoR / DoD |  | 4 |  |  | Yes |  |  | Included | Discovery
PM-2.6 | Discovery kickoff |  | 6 |  |  | Yes |  |  | Included | Discovery
PM-3 | Discovery deliverables
PM-3.1 | Project Charter |  | 6 |  |  | Yes |  |  | Included | Discovery
PM-3.2 | Daily comms with team |  | 3 |  |  | Yes |  |  | Included | Discovery
PM-3.3 | Discovery metrics setup |  | 4 |  |  | Yes |  |  | Included | Discovery
PM-3.4 | Vision & Scope review/coordination |  | 10 |  |  | Yes |  |  | Included | Discovery
PM-3.5 | Initial product backlog support |  | 8 |  |  | Yes |  |  | Included | Discovery
PM-3.6 | Feature-based estimation oversight |  | 24 |  |  | Yes |  |  | Included | Discovery
PM-3.7 | Initial budget estimation |  | 4 |  |  | Yes |  |  | Included | Discovery
PM-3.8 | Initial dev phase plan |  | 4 |  |  | Yes |  |  | Included | Discovery
PM-3.9 | Resource plan |  | 2 |  |  | Yes |  |  | Included | Discovery
PM-3.10 | Initial risk matrix |  | 3 |  |  | Yes |  |  | Included | Discovery
PM-3.11 | Internal demo / proposal review |  | 4 |  |  | Yes |  |  | Included | Discovery
PM-3.12 | Update proposal for customer |  | 4 |  |  | Yes |  |  | Included | Discovery
PM-4 | Implementation — recurring
PM-4.1 | Sprint planning / refinement / retro |  | 8 |  |  | No |  |  | Included | Implementation |  | Per sprint over implementation duration
PM-4.2 | Status reporting (weekly) |  | 4 |  |  | No |  |  | Included | Implementation
PM-4.3 | Risk & issue management |  | 4 |  |  | Yes |  |  | Included | Implementation
PM-4.4 | Change request management |  | 4 |  |  | Yes |  |  | Included | Implementation
PM-4.5 | Stakeholder demos / acceptance |  | 4 |  |  | No |  |  | Included | Implementation
PM-4.6 | Project closure |  | 8 |  |  | No |  |  | Included | Implementation

## UIUX Estimation
UI/UX Estimation
Purpose: | UI/UX WBS — design audit, IA, wireframes, design system, per-epic screens, prototyping iterations, accessibility review, dev hand-off.
How to use: | (1) Front-load Discovery items (audit, IA, wireframes, design system). (2) Add or remove epics from the Implementation block to match WBS and Estimates. (3) Apply Contingency = Yes on items requiring stakeholder reviews (wireframes, design system).
Inputs: | O/ML/P per row, Apply Contingency Y/N, Include, Phase, Deliverable, Description.
Outputs: | UX roll-up flows to Buffers and Headcount and Cost.
Linked tabs: | Buffers & Non-Dev Activities (UI/UX roll-up). Headcount and Cost.
Default contingency: | 0.2 | (used when Apply Contingency = Yes; multiplied by Most Likely)
UI/UX deliverables are typically front-loaded in Discovery; keep an Implementation tail for hand-off and iteration.
ID | Service / Activity | Optimistic | Most Likely | Pessimistic | Expected | Apply Contingency | Contingency | Final Expected | Include | Project Phase | Deliverable | Description / Scope | Assumptions | Notes
| TOTALS | [7 empty] | (only Included counted at right)
UX-1 | Discovery
UX-1.1 | Design audit / heuristic review | 8 | 16 | 24 |  | No |  |  | Included | Discovery
UX-1.2 | User research / personas | 16 | 24 | 40 |  | No |  |  | Not included | Discovery
UX-1.3 | Information architecture | 8 | 16 | 24 |  | No |  |  | Included | Discovery
UX-1.4 | Wireframes (key flows) | 16 | 32 | 48 |  | Yes |  |  | Included | Discovery
UX-1.5 | Design system / tokens | 16 | 32 | 48 |  | Yes |  |  | Included | Discovery
UX-2 | Implementation — per epic
UX-2.1 | Authorization screens | 8 | 12 | 20 |  | No |  |  | Included | Implementation
UX-2.2 | Profile screens | 8 | 16 | 24 |  | No |  |  | Included | Implementation
UX-2.3 | Wallet screens | 16 | 32 | 48 |  | Yes |  |  | Included | Implementation
UX-2.4 | Admin panel screens | 8 | 16 | 24 |  | No |  |  | Included | Implementation
UX-2.5 | Notifications / feedback states | 4 | 8 | 12 |  | No |  |  | Included | Implementation
UX-2.6 | Dev hand-off / specs | 8 | 16 | 24 |  | No |  |  | Included | Implementation
UX-2.7 | Prototype iterations | 4 | 8 | 16 |  | No |  |  | Included | Implementation
UX-2.8 | Accessibility review | 4 | 8 | 16 |  | No |  |  | Included | Implementation

## Buffers & Non-Dev Activities
Buffers & Non-Dev Activities
Purpose: | Applies the project-wide PERT Z-score buffer to dev hours, then adds Bugfix / Documentation / Communication coefficients. Derives Manual QA & AQA from BE+FE (with variance now correctly propagated, fixing a v1.4 bug). Rolls up discipline-tab Final Expected sums (BA / Arch / DevOps / PM / UI-UX / QA-from-tab).
How to use: | (1) Set Z-Score (cell B2) to 0 (50% CI), 1 (84% CI) or 2 (97% CI). Higher = more conservative. (2) The dev rows pull subtotals (Expected) and variance (sum-of-variance per row) from WBS and Estimates. (3) Coefficients (Bugfix 12%, Documentation 5%, Communication 10%, MQA 15%, AQA 15%) come from Input Data named ranges. Edit there. (4) 'Treat BE as FullStack' (cell K6) merges FE into BE if your team is full-stack. (5) Discipline roll-ups at the bottom use SUMIF over each discipline tab's 'Included' rows.
Inputs: | Z-Score, Treat BE as FullStack, Input Data coefficients. WBS Expected & Variance from WBS and Estimates. Discipline tab Final Expected.
Outputs: | Grand Total per role (col L) — feeds the 'Estimated Hours' column on Headcount and Cost.
Linked tabs: | WBS and Estimates (input). Input Data (coefficients). All 6 discipline tabs (roll-ups). Headcount and Cost (consumer).
Z-Score (0..2) | 1 | 0 = 50%, 1 = 84%, 2 = 97% confidence interval
Role | Subtotal, h | Variance, h | StdDev, h | Z-Score | Dev & Test Buffered, h | Bugfix, h | Documentation, h | Communication, h | Total, h | Treat BE as FullStack | Grand Total, h
Back-End | [9 empty] | FALSE
Front-End
Manual QA | [5 empty] | 0
AQA | [5 empty] | 0
Pulled from discipline tabs (Final Expected, Included only)
BA
Architecture
DevOps
PM
UI/UX
QA (alt: from QA tab)

## Rates
Rates — Role x Seniority x Location rate card
Purpose: | External rate card. Headcount and Cost and Maintenance look up the per-hour rate by matching a resource's (Role, Seniority, Location) triple here.
How to use: | (1) Add rows by INSERTING between existing rows (do not append at the bottom — formulas reference whole columns; appending is fine but inserting keeps things tidy). (2) The triple (Role, Seniority, Location) is the key — keep names IDENTICAL to those used on Headcount and Cost. (3) If a resource's triple does not match any row, the cost formula falls back to RefRate ($/h) on Input Data.
Inputs: | Manual rate entries.
Outputs: | Rate, $/h consumed by Headcount and Cost and Maintenance via INDEX/MATCH.
Linked tabs: | Headcount and Cost. Maintenance. Internal Cost & Profitability (informational).
Role | Seniority | Location | Rate, $/h
DM | M2 | Poland | 62
PM | M1 | Poland | 55
Solution Architect | S1 | Poland | 95
Software Architect | S1 | Poland | 85
BA | S1 | Poland | 53
UI/UX | M3 | Poland | 50
Front-End Web | Lead | Poland | 72
Front-End Web | M1 | Poland | 50
Front-End Mobile | S1 | Poland | 55
Back-End | S1 | Poland | 75
Back-End | M2 | Poland | 55
Back-End | J2 | Poland | 48
Blockchain / Crypto | S1 | Poland | 120
Manual QA | S1 | Poland | 47
Manual QA | M1 | Poland | 42
Manual QA | J1 | Poland | 33
AQA | M2 | Poland | 50
DevOps | S1 | Poland | 70

## Input Data
Input Data — global coefficients, blended-rate fallback, enums
Edit the values in column B. The whole workbook references these named cells.
Coefficients
RefUnitTest | 20% | WBS augmentation: unit-test overhead as fraction of base hours
RefIntegrationTest | 10% | WBS augmentation: integration-test overhead
RefCodeReview | 10% | WBS augmentation: code review overhead
RefManualQA | 30% | Manual QA hours = (BE+FE) * this
RefAQA | 15% | Automation QA hours = (BE+FE) * this
RefBugFix | 10% | Buffer: bugfix hours = Dev * this
RefDocumentation | 7% | Buffer: documentation hours = Dev * this
RefCommunication | 8% | Buffer: communication hours = Dev * this
RefRate | 60 | Blended-rate fallback used when role lookup misses
Enums (data-validation source lists)
|  |  | EnumRoles | EnumSeniorities | EnumPhase | EnumLocations | EnumYesNo | EnumInclude
|  |  | DM | J1 | Discovery | Poland | Yes | Included
|  |  | PM | J2 | Design | Ukraine | No | Excluded
|  |  | Solution Architect | M1 | Build | USA
|  |  | Software Architect | M2 | Test | EU
|  |  | BA | M3 | Launch | Remote
|  |  | UI/UX | S1 | Stabilization
|  |  | Front-End Web | Lead
Front-End Mobile
Back-End
Blockchain / Crypto
Manual QA
AQA
DevOps

## Internal Cost & Profitability
Internal Cost & Profitability
Purpose: | Margin model. Per resource, computes Internal Cost / month (salary + social tax + overhead) and Profit / month (External Rate * Hours/mo - Internal Cost). Project Profitability rolls up against Headcount and Cost Total Cost.
How to use: | (1) Edit per row: Role / Seniority / External Rate / Avg Salary (gross monthly) / Internal Rate (informational) / Social Tax % / Overhead. Hours/mo defaults to 168 (=21 days * 8h). (2) Project Profitability cell at the bottom = (Headcount and Cost Total Cost - Sum Internal Cost) / Total Cost. Aim for 15-25% on standard work, more on high-risk fixed-price. (3) Seniority Index at the bottom shows team seniority relative to RefRate; > 1 means more senior than the blended baseline.
Inputs: | External rate, avg salary, social tax %, overhead, hours/month per resource (manual). Headcount and Cost Total Cost.
Outputs: | Internal cost per resource, project total internal cost, project profitability %, seniority index. Reported on Check-list mandatory calculations.
Linked tabs: | Rates (cross-check on external rate). Headcount and Cost (Total Cost). Check-list (mandatory KPIs).
Role | Seniority | External Rate, $/h | Avg Salary, $/mo | Internal Rate, $/h | Social Tax % | Overhead, $/mo | Hours/mo | Internal Cost, $/mo | Profit, $/mo | Profit %
DM | M2 | 62 | 6000 | 35.71 | 0.1 | 2542 | 168
PM | M1 | 55 | 3000 | 17.86 | 0.1 | 2542 | 168
Solution Architect | S1 | 95 | 8414 | 50.08 | 0.1 | 2542 | 168
Software Architect | S1 | 85 | 7446 | 44.32 | 0.1 | 2542 | 168
BA | S1 | 53 | 5040 | 30 | 0.1 | 2542 | 168
UI/UX | M3 | 50 | 2800 | 16.67 | 0.1 | 2542 | 168
Front-End Web Lead | Lead | 72 | 4305 | 25.63 | 0.1 | 2542 | 168
Front-End Web | M1 | 50 | 1909 | 11.36 | 0.1 | 2542 | 168
Front-End Mobile | S1 | 55 | 4334 | 25.8 | 0.1 | 2542 | 168
Back-End Lead | S1 | 75 | 5275 | 31.4 | 0.1 | 2542 | 168
Back-End | M2 | 55 | 3936 | 23.43 | 0.1 | 2542 | 168
Back-End Junior | J2 | 48 | 1500 | 8.93 | 0.1 | 2542 | 168
Blockchain | S1 | 120 | 16800 | 100 | 0.1 | 1596 | 168
Manual QA Lead | S1 | 47 | 3544 | 21.1 | 0.1 | 2542 | 168
Manual QA | M1 | 42 | 1521 | 9.05 | 0.1 | 2542 | 168
Manual QA Junior | J1 | 33 | 962 | 5.73 | 0.1 | 2542 | 168
DevOps | S1 | 70 | 6368 | 37.9 | 0.1 | 2542 | 168
Project Totals
Project Profitability (build) |  | (Total Cost - Sum Internal Cost) / Total Cost
Seniority Index (avg) |  | ratio of avg ext rate to fallback blended rate

## Headcount and Cost
Headcount and Cost — Resource allocation grid
Purpose: | The single source of truth for staffing. Each row is one resource with Role / Seniority / Location / Headcount / Allocation / Start & End Week. Allocated Hours and Allocated Cost are computed; rate is looked up on the Rates tab. The right-hand 'Estimated vs Allocated' panel reconciles allocation against the discipline totals computed on Buffers.
How to use: | (1) For each resource, COPY a sample row and modify. Multiple rows with the same Role are supported (e.g. 5 BE seniors + 3 BE mids). (2) Headcount = number of physical people. Allocation = % of full time (1.0 = 100%). FTE = Headcount * Allocation (computed). (3) Start Week / End Week define when the resource is on the project; Duration = End - Start + 1; Allocated Hours = Duration * FTE * 40. (4) Allocated Cost looks up rate via INDEX/MATCH on (Role, Seniority, Location); falls back to RefRate ($/h on Input Data) if no rate row matches. (5) The 'Delta Hours' column on the right shows over/under allocation per role. Aim to keep ¦Delta¦ small relative to Estimated.
Inputs: | Per-resource Role/Seniority/Location/Headcount/Allocation/Start/End. Rates tab. Input Data RefRate fallback. Buffers Grand Total per role (Estimated Hours).
Outputs: | Total Hours, Total Cost, Peak Headcount, Peak FTE, Duration Weeks. Per-row Allocated Cost feeds Monthly Cost Roll-out and Internal Cost & Profitability.
Linked tabs: | Rates (rate lookup). Buffers & Non-Dev Activities (Estimated hours). Monthly Cost Roll-out. Internal Cost & Profitability.
Project Summary | [10 empty] | Role | Estimated Hours | Allocated Hours | Allocated FTE | Delta Hours | Remaining FTE | Remaining Weeks
Peak Headcount | [10 empty] | Back-End
Peak FTE | [10 empty] | Front-End
Duration Weeks | [10 empty] | Manual QA
Total Hours | [10 empty] | AQA
Total Cost | [10 empty] | BA
Avg Rate (blended) | [10 empty] | Architecture (SA+SwA)
DevOps
PM
Resources (enter by copying a row, then edit) | [10 empty] | UI/UX
Role | Headcount | Allocation | FTE | Start Week | End Week | Duration | Allocated Hours | Allocated Cost | Seniority | Location
Back-End | 5 | 1 |  | 1 | 8 |  |  |  | S1 | Poland
Back-End | 3 | 1 |  | 3 | 8 |  |  |  | M2 | Poland
Front-End Web | 1 | 1 |  | 1 | 4 |  |  |  | Lead | Poland
Front-End Mobile | 1 | 1 |  | 1 | 8 |  |  |  | S1 | Poland
Manual QA | 1 | 1 |  | 1 | 8 |  |  |  | S1 | Poland
Manual QA | 1 | 0.5 |  | 1 | 8 |  |  |  | M1 | Poland
AQA | 1 | 0.5 |  | 1 | 8 |  |  |  | M2 | Poland
PM | 1 | 0.5 |  | 1 | 8 |  |  |  | M1 | Poland
BA | 1 | 0.5 |  | 1 | 8 |  |  |  | S1 | Poland
Solution Architect | 1 | 1 |  | 1 | 8 |  |  |  | S1 | Poland
UI/UX | 1 | 1 |  | 1 | 3 |  |  |  | M3 | Poland
DevOps | 1 | 1 |  | 1 | 8 |  |  |  | S1 | Poland

## Monthly Cost Roll-out
Monthly Cost Roll-out
Purpose: | Cash-flow / spend curve. Spreads each resource's Allocated Cost across calendar months proportional to the weeks of [Start Week, End Week] that fall in each month (month width = 4.33 weeks).
How to use: | (1) The first 12 sample rows mirror the seeded resources on Headcount and Cost. (2) When you add resources there, copy a row here and update the row index in the 'Headcount and Cost' references. (3) The TOTAL row at the bottom gives spend per month — useful for cash-flow conversations and to validate the project duration.
Inputs: | Allocated Cost, Start Week, End Week, Duration from Headcount and Cost.
Outputs: | Per-resource and total spend by month (M1 .. M18).
Linked tabs: | Headcount and Cost (single source of staffing & cost).
Resource (from Headcount and Cost) | Total Allocated, $ | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18
TOTAL

## Fixed Costs
Fixed / 3rd-party Costs
Purpose: | Lump-sum costs not modeled per FTE-hour: penetration testing, performance testing, smart contract audit, compliance officer, technical writer, KYC/AML licenses, cloud bill estimates.
How to use: | (1) Add a line per cost. (2) Set Include = Included to add it to the SOW total, Not included to keep it visible but excluded, Post-MVP to defer, Select for decision pending. (3) Use the Notes column to point to the vendor quote. (4) Cloud cost lines: pull values from the DevOps Estimation tab cost-modelling outputs.
Inputs: | Manual entries (item, amount, vendor, notes, include).
Outputs: | 'Total Included' at the bottom — add to SOW external total beside Headcount and Cost Total Cost.
Linked tabs: | DevOps Estimation (cloud cost estimates feed this tab). Headcount and Cost (Total Cost is the FTE side; this tab is the non-FTE side).
Item | Amount, $ | Vendor / supplier | Notes | Include
Penetration testing | 35000 |  | external pen-test before go-live | Included
Performance / load testing | 20000 |  | JMeter / k6 partner | Included
Compliance Officer (per audit) | 20000 |  | GDPR / PCI-DSS sign-off | Not included
Technical Writer | 20000 |  | user docs + admin guide | Not included
Smart Contract Audit | 15000 |  | if blockchain components | Not included
3rd-party KYC / AML licenses | 0 |  | Onfido, SumSub, Veriff | Select
Cloud cost (Discovery) | 0 |  | estimate from DevOps tab | Included
Cloud cost (Implementation) | 0 |  | estimate from DevOps tab | Included
Cloud cost (1st year prod) | 0 |  | estimate from DevOps tab | Included
Total Included

## Maintenance
Maintenance / Run-rate Cost (post go-live)
Purpose: | Steady-state monthly cost grid for support / minor enhancements after go-live. Same role pattern as Headcount and Cost but with monthly cadence (168 h/mo per FTE).
How to use: | (1) For each role you'll keep on retainer, set Headcount and Allocation. (2) Rate is looked up from the Rates tab. (3) The Annual Run-rate cell at the bottom is what you quote in the SOW maintenance section. (4) If the deal is fixed-price-with-SLA, also discuss Fixed Costs (cloud bill, monitoring, security tooling) — they aren't here.
Inputs: | Per-role Headcount, Allocation, Seniority, Location. Rates tab.
Outputs: | Monthly Run-rate, Annual Run-rate.
Linked tabs: | Rates (rate lookup). Headcount and Cost (build phase counterpart). Fixed Costs (non-FTE recurring costs).
Role | Seniority | Location | Headcount | Allocation | FTE | Hours/Month | Rate, $/h | Monthly Cost, $
PM | M1 | Poland | 1 | 0.25
Back-End | S1 | Poland | 1 | 0.5
Front-End Web | M1 | Poland | 1 | 0.25
Front-End Mobile | S1 | Poland | 1 | 0.25
Manual QA | M1 | Poland | 1 | 0.5
DevOps | S1 | Poland | 1 | 0.5
BA | S1 | Poland | 1 | 0.1
Solution Architect | S1 | Poland | 1 | 0.1
Monthly Run-rate Total
Annual Run-rate

## Epic Weight
Epic Weight (Build cost ranking)
Purpose: | The 'where does the money go?' view. Sums Expected Implementation BE+FE per epic from WBS and Estimates, multiplied by RefRate, and ranks epics by cost.
How to use: | (1) The Epic ID column matches against the LEFT of WBS column B (ID). Add a row per epic; epic prefix must match the ID format used on WBS (e.g. 'E-1', 'INF'). (2) Cost is blended (BE+FE Expected hours * RefRate). For role-aware cost split, build a custom view from Headcount and Cost. (3) % of build column is share of total — useful in client conversations.
Inputs: | Epic IDs (manual). WBS and Estimates Expected BE/FE columns. RefRate.
Outputs: | Per-epic build cost and % of total. Sort the table after totals are calculated to rank.
Linked tabs: | WBS and Estimates (data source). Input Data (RefRate).
Epic ID | Epic Name | BE Hours | FE Hours | Cost (blended), $ | % of build
INF | Infrastructure & Foundations
E-1 | Authorization
E-2 | Profile Management
E-3 | Wallet
Total

## WBS Comparison
WBS Comparison (snapshot vs current)
Purpose: | Tracks scope creep between estimate versions. Stores up to two snapshots side-by-side and computes deltas vs. the current WBS, joined by ID.
How to use: | (1) PASTE the v1 snapshot BE/FE hours in cols C-D against each ID. (2) Optionally paste a v1.1 snapshot in cols E-F. (3) Current BE/FE columns auto-pull from WBS and Estimates by ID match. (4) Δ columns show the change. (5) When a new version starts, snapshot the current numbers into the v1.1 cols (paste-as-values), then move v1.1 to v1 and clear v1.1.
Inputs: | Snapshot pastes (manual). WBS and Estimates Expected BE/FE.
Outputs: | Δ BE / Δ FE per row.
Linked tabs: | WBS and Estimates.
ID | Decomposition Item | v1 BE | v1 FE | v1.1 BE | v1.1 FE | Current BE | Current FE | Δ (BE) | Δ (FE)
INF-1.1 | Solution setup (repos, project templates)
INF-1.2 | Local infrastructure setup
INF-1.3 | CI/CD setup
INF-1.4 | Static code analysis
US-1.1 | Onboarding
US-1.2 | Accept Terms of Use
US-1.3 | Sign Up (email/phone/SSO)
US-1.4 | Login
US-1.5 | Reset password
US-1.6 | Logout
US-1.7 | 2FA setup
US-2.1 | View profile info
US-2.2 | Edit personal details
US-2.3 | Change password
US-2.4 | Manage notification preferences
US-2.5 | Delete account
US-3.1 | Setup wallet
US-3.2 | Buy tokens
US-3.3 | Sell tokens
US-3.4 | View transactions
US-3.5 | KYC initiate / upload ID / verify